## Sheet1
Date | Task Number | Task Name | Hours | Description
Design of Convert and Compare Program |  |  | 68 | Hours spent
About:
Program to convert and compare files
Redefines old compare transit program
Software(Amar Sarvepalli - under works 2013,in C++11)
| 9999 | Documentation | 24
|  |  | 4 | Design Approach Memo
|  |  | 4 | Code Document (setting up the complier, opening the project, reading the class and building the exectuable) and Code documentation on CLASS and Methods
|  |  | 16 | User's Guide
2013-11-08 | 1 | Review of old CompareTransit program | 8 | Task Total
2013-11-08 | -> | Reviewed the original application | 2 | Application Review:
2013-11-09 | -> | Reviewed the source code |  | Software(written in 2007, in C++98)
2013-11-09 | -> | Setup of the new C++11 version |  | Uses predefied fixed formats (such as text and DBF files)
2013-11-09 | -> | Current limitations |  | Uses predefined data types and user should provide the input files in only this format (field width and type)
Checks only predefined attibutes (hardcoded in the source code)
Cannot change the field names
TCAD: User need to export both ROUTE and STOP files to DBF and then process the fields to predefined field types
CUBE: Process whitespaces between the keywords, wrapped lines as different between the itineraries
TRANPLAN: same limitations as in CUBE
Limited to route files only.
Expects predefiend attributes in predefined data types and names
Works only for the predefined attributes.
Limitted to only two files (base<file1> and compare<file2>)
|  |  | 3 | Source Code Review:
Missing complete source code (missing main class or readDBF format class)
No common strucutre : Each process (TRANPLAN, CUBE, TCAD and EMME) is a complete new class.
No read formats class: Uses predefined DFB library to read TCAD DBF files and is not part of main
No extendable classes: Only one class -Route network, which is defined in four differnt ways (one for each formats,not mutable)
No datatable class : No datatable class, data is read in only route class and process from there
No compare itinerary class : No such common class. Each format based route classes are compared in their repective main().
No string processing : No string split class, trim class or remove whitespace class
|  |  | 1 | Need for Upgrade:
Well, need to include newer formats such as (GTFS, which is in *.CSV file)
Our work beyond NewStarts applications, where we need a simple file comparison method
(without exporting to Excel readable formats and writing some compare formulas across fields)
Comparions during the development phase: Whether it is the model estimation, or calibration or other taks,
there is no easy way to compare a few fields between files to get a sense of what's different
Sceanrio management: Need an easy tool to compare model inputs between two scenarios or same file across mutiple scenarios
|  |  | 2 | Software Setup: download and setup a new 11C++ compiler
2013-11-09 | 2 | Design New Approach | 18 | Task Total
2013-11-15 | -> | Added required structure | 2 | Current and Future Requirements:
2013-11-10 | -> | Thoughts on where we want to go with this |  | GUI: Must have a Graphic User Interface
2013-11-16 | -> | Revised approach to include a convertor |  | Native formats: User should be ableto specify existing formats such as *.rts, *.bin for tcad
2013-11-16 | -> | Design adjustments for convertor |  | GTFS: need to include to GTFS (*.csv or *.txt based formats)
2013-11-16 | -> | Extended thought for *.DBF & *.FFA |  | More than Transit Files: Feature to compare other table types: model-parameter, se-data and highway attributes
2013-11-16 | -> | Notes on design guide |  | Multiple file specification: User should be able to specify more than two files (base<file1> and compare<file2>)
Two-way compare: User should be able to do
1) SAME type of file across muliple scenarios (<file1>, <file2>, <file3>, ...<fileN>)
2) DIFFERENT set of files across two scenarios(ex: Scenario-A {<file1>, <file2>,....<fileN>}, Scenario-B {<file1>, <file2>,....<fileN>})
Here,<file1> from Scenario-A is compared to <file1> from Scenario-B
Cross Platfroms: Not that we need but by default, should work on WindowsXP, Windows7, Windows8, Mac and Fedora (open OS).
|  |  | 8 | GUI Design: Design broken down into five PARTS
PART-0: Process
Process_Type(radio buttons: 1.Compare Files, 2.Export tcad and other (*.bin), cube(*.dbf), cube(any except dbf), files to CSV)
PART-A: FileTypeandFormat
File_Type (General: Model tables, SEDATA tables and other simple txt or CSV or BIN files)
(Transit: compares route and stop attributes)
(Highway: compares network attributes)
File_Formats (dropdown menu: DBF, CSV, TXT, TRANPLAN, TPPLUS, CUBE-TRNBUILD, CUBE-PT, TCAD, EMME2, EMME3 and GTFS)
PART-B: ComparisonType
Type_of_comparison(check box: 1) one file type across multiple scenarios, 2) several file types between two scenarios)
Number_of_Files(dropdown menu: {1 - 10})
More_than_10_Files(check box: this allows user to specify custom compare.CTL files, and disables SAVE)
PART-C: FileSpecifications
inFile_specification: Label<file1> Box<displayBrowsedFileName> Button<browse>
Label: shows file number
Box : Dispalys file name after selecting or by default shows "specify file1"
Button: Opens windows file browser to look for Extension based on PART-A choices
Extension chooser:
PART-A: File_Type File_Formats Extension
General or Highway BIN *.bin
General or Highway CSV *.csv
General or Highway TXT *.txt
General or Highway DBF *.dbf
Transit CSV *.csv
Transit TXT *.txt
Transit DBF *.DBF
Transit TCAD *.rts
Transit CUBE-PT *.lin
Transit CUBE-TRNBUILD *.* (all since no specific extentsion)
Transit TPPLUS *.* (all since no specific extentsion)
Transit TRANPLAN *.* (all since no specific extentsion)
Transit EMME2 *.* (Not sure)
Transit EMME3 *.* (Not sure)
Transit GTFS *.txt
outFile_specification: Label<fileName> Box<displayBrowsedFileName> Button<browse> CheckBox<outputMultipleFiles>
CheckBox: This option exists only for PART-B > OPTION-2, where the we want to see separateoutput for different filetypes.
This split into two sections (SET-A: left side and SET-B: rightside)
Each section has upto 10 file specifications
PART-B > OPTION-1: Always enables SET-A (left side) but limits the number of inFile_specification to Number_of_Files
PART-B > OPTION-2: Enables only SET-B (left side) but limits inFile_specification by Number_of_Files
PART-D: GUI Settings
SAVE settings (button to save current choices to Compare.CTL)
LOAD settings (button to load previously saved Compare.CTL)
RSET settings (button to clear out all current settings, back to default)
COMPARE (button to run the compare data)
CLOSE settings(button to close and exit the program, this also kills the program if something goes wrong)
Outputs: The number of outputs files directly correspond to Number_of_Files. However, the contents vary by PART-B > OPTIONS
PART-B > OPTION-1: This is a many-to-many comparison. For example, if user specifies 10 files, then it compares 90 datatables
output <file1> contains comparison of <file1> with all remaining files (<file2...file10>
output <file2> contains comparison of <file2> with all remaining files (<file1,file3...file10>
PART-B > OPTION-2: This is a one-to-one comparison. For example, if user specifies 10 files in SET-A and 10 files in SET-B,
output <file1> contains comparison of SET-A<file1> to SET-B<file1>, only one table comparison
output <file2> contains comparison of SET-A<file1> to SET-B<file1>, only one table comparison
|  |  | 8 | Design Approach:
Converter: Converts differnt formats into CSV fileformat.
Tables to use field structure (vector<fieldType>fields and array fields)
CLASSES:
Level:0 CLASS: Converter (reads Compare.CTL and converts all specified files to *.csv files,
routes are split into _Routes.csv and _Stops.csv)
Level:0 CLASS: Compare (reads Compare.CTL, CompareFieldInfo, creates either
1) builds TableData & CompareTableData & SummaryStats or
2) builds BuildRouteTable & CompareRouteItinerary)
Level:1 CLASS: ReadCTLFile (reads the control file and gets the user settings)
Level:1 CLASS: CompareFieldInfo
Level:1 CLASS: ExportBINToCSV (simply exports binary file to csv formats)
Level:1 CLASS: ExportDBFToCSV (simply exports DBF file to csv formats)
Level:1 CLASS: ExportCUBEToCSV (simply exports cube trasnit line files to csv formats)
Level:1 CLASS: OutputReport (writes output to the file,include methods, write.csv and write.txt)
Level:1 CLASS: BuildTableData (array of fields with row elements, converts vector<dataType> array<dataType> and methods to get & set data to these fields)
Level:1 CLASS: BuildRouteTable (builds route table with ID,Name,mode,Headway1,Headway2,Headway3,Fare<optional>,Stops,Nodes,Delay(same number as stops)
Level:1 CLASS: CompareDataTables (creates a third table and reports differnces between the two tables)
Level:2 CLASS: CompareRouteItinerary(specific to transit where node/stops info is appended to lines)
Level:2 CLASS: CompareGeneralData (compares all common fields) between two or more files
Level:2 CLASS: SummaryStats(computes, column sums, min and maximum value and count(not null), returns the position of row with pmin and pmax)
Level:3 CLASS: ReadFormats (on transit side: identifies the file extension and looks for header files)
Level:4 CLASS: ReadBINFile (reads binary files, relies on DCB file for header info and creates vector<dataType> for each field)
Level:4 CLASS: Read_TCAD_Routes (reads transit lines and stops, tagged nodes)
Level:4 CLASS: Read_TRNBUILD_Routes (reads transit lines and stops,nodes and stop delay, optional keywords)
Level:4 CLASS: Read_PT_Routes (reads transit lines and stops,nodes and stop delay, optional keywords)
Level:4 CLASS: Read_TPPLUS_Routes (reads transit lines and stops,nodes and stop delay, optional keywords)
Level:4 CLASS: Read_TRANPLAN_Routes (reads transit lines and stops,nodes and stop delay)
Level:4 CLASS: Read_EMME2_Routes (reads transit lines and stops,nodes and stop delay, optional keywords)
Level:4 CLASS: Read_EMME3_Routes (reads transit lines and stops,nodes and stop delay, optional keywords)
Level:4 CLASS: Read_GTFS_Routes (reads transit lines and stops,nodes and stop delay)
Level:5 CLASS: ReadDCBFile (filename extracted from main binary file and returns field names, field types and field bytes)
Level:5 CLASS: ReadBINFile (filename extracted from main binary file and returns field names, field types and field bytes)
Level:5 CLASS: ReadCSVFile
Level:5 CLASS: ReadDBFFile
Level:5 CLASS: ReadTXTFile (route files)
Level:5 CLASS: ReadFFTFile (fixedformat text, uses 3 spaces to determine the field break point)
Level:5 CLASS: WriteTableData (writes out table data from both routeTable(Route and Stop) and dataTable)
Utility Classes:
Level:6 CLASS: StringProcess (split, trim, remove whitespaces and replace space with underscore)
Level:6 CLASS: ConvertVectorToArray (converts vector<dataType> Array<dataType>
2013-11-15 | 3 | Creating Classes | 20
2013-11-16 | Helper Classes | StringProcessor(4 hours) | 4 | Create CLASS: StringProcess (split, trim, remove whitespace and replace space with underscore)
2013-11-17 |  | VectorToArray(2 hours) | 2 | Create CLASS: ConvertVectorToArray (converts vector<dataType> Array<dataType>
| Read File Classes | Each class takes about 1 day to write | 2 | Create CLASS: ReadDCBFile
|  | BIN (1 day) | 2 | Create CLASS: ExportBINToCSV
|  | DCB (2 hours) | 8 | Create CLASS: ReadBINFile (info from ReadDCBFile, Reads Binary file contents)
CSV (parse data) & TXT (1 day)
|  | DBF (1 day) | 2
2013-11-23 | 2 | Creating Classes | 18
2013-11-23 | Read File Classes | BIN (file to CSV) Complete | 8 | First distributable program (BIN2CSV.exe)
2013-11-23 |  | BIN file (character width increase to 100) | 2 | Fixed the character length issue
2013-11-24 |  | Read DBF File | 8 | Create CLASS: DBF to CSV
2013-11-28 | 2 | Creating Classes | 4
2013-11-28 |  | Sample GUI in QT | 2
|  | GUI Description in PPT | 2